## Summary
| CAP 350 - Data Engineering - Capstone Project | Ontime
| ETL, Data Analysis and Visualization | ETL_DAV_Module
| Functional Requirement 2.1 - Transaction Details Module | REQ2.1_Module
| Functional Requirement 2.2 - Customer Details Module | REQ2.2_Module
| Overall progress of the Testing | Ontime
| Total number of test cases | 100
| Number of testers | 1
| Test cycle duration | 5 days
Status for
Number of test cases planned
Number of test cases executed
Number of test cases executed overall
Number of defects encountered today
Number of defect encountered so far
Number of critical defects- still open
Overall status
Number of test cases planned
Number of test cases executed
Pass Percentage of the defects
Defects density
Critical defects percentage

## Detailed status
Module | Scenarios | Test Description | Complexity | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/Partially Tested) | Additional Comments
ETL1.1 | Customer Info Table FIRST_NAME | First name to be displayed in Title case | Low | 2023-10-05 | Pass
ETL1.1 | Customer Info Table MIDDLE_NAME | Middle name to be displayed in lower case | Low | 2023-10-05 | Pass
ETL1.1 | Customer Info Table LAST_NAME | Last name to be displayed in Title case | Low | 2023-10-05 | Pass
ETL1.1 | Customer Info Table FULL_STREET_ADDRESS | Concatenate Street name and Apartment number with a comma | Low | 2023-10-05 | Pass
ETL1.1 | Customer Info Table CUST_PHONE | Change the format of phone number to (XXX)XXX-XXXX | Medium | 2023-10-05 | Pass
ETL1.1 | Branch Table BRANCH_ZIP | If the source value is null load default (99999) value else Direct move | Medium | 2023-10-05 | Pass
ETL1.1 | Branch Table BRANCH_PHONE | Change the format of phone number to (XXX)XXX-XXXX | Medium | 2023-10-05 | Pass
ETL1.1 | Credit Card Table TIMEID | Convert DAY, MONTH, and YEAR into a TIMEID (YYYYMMDD) | Medium | 2023-10-05 | Pass
ETL1.2 | Database name | Check the Database name created as creditcard_capstone | Low | 2023-10-05 | Pass
ETL1.2 | Tables should be created by the following names in RDBMS: CDW_SAPP_BRANCH CDW_SAPP_CREDIT_CARD CDW_SAPP_CUSTOMER | Check the Table names to be matched as given in the REQ 1.2 - CDW_SAPP_BRANCH CDW_SAPP_CREDIT_CARD CDW_SAPP_CUSTOMER | Low | 2023-10-05 | Pass
REQ2.1 1 | Used to display the transactions made by customers living in a given zip code for a given month and year. Order by day in descending order. | Verify the length of Zipcode provided by the customer is valid | Low | 2023-10-10 | Version2 | Tested with ideal conditions
REQ2.1 1 | Used to display the transactions made by customers living in a given zip code for a given month and year. Order by day in descending order. | Verify the Zipcode doesn't contain all Zeros | Low | 2023-10-10 | Version2 | Tested with ideal conditions
REQ2.1 1 | Used to display the transactions made by customers living in a given zip code for a given month and year. Order by day in descending order. | Verify the Year and Month in YYYY and MM format | Medium | 2023-10-10 | Version2 | Tested with ideal conditions
REQ2.1 1 | Used to display the transactions made by customers living in a given zip code for a given month and year. Order by day in descending order. | Verify the result should be sorted in Descending order | Medium | 2023-10-10 | Pass
REQ2.1.2 | Used to display the number and total values of transactions for a given type | Verify that all the Transactiontypes are listed for the Customer to select from | Medium | 2023-10-12 | Pass
REQ2.1.2 | Used to display the number and total values of transactions for a given type | Verify that based on the selection, the output is matching with the selection type. | Medium | 2023-10-12 | Pass
REQ2.1.2 | Used to display the number and total values of transactions for a given type | Verify that the total value of Transaction is the aggregate summing of all the Transactions | Medium | 2023-10-12 | Pass
REQ2.1.3 | Used to display the total number and total values of transactions for branches in a given state. | Verify that the length of the State code provided by the user is 2 | Medium | 2023-10-12 | Pass | Tested with ideal conditions
REQ2.1.3 | Used to display the total number and total values of transactions for branches in a given state. | Verify that the State code provided by the user is not numeric | Medium |  | Version2 | Tested with ideal conditions
REQ2.2.1 | Used to check the existing account details of a customer. | Verify that the SSN provided is 4 digits(last) | Medium |  | Version2
REQ2.2.1 | Used to check the existing account details of a customer. | Verify to format the last name provided by the customer is of Title case | Medium | 2023-10-12 | Pass
REQ2.2.1 | Used to check the existing account details of a customer. | Verify that output displayed is only the account asked for | Medium | 2023-10-12 | Pass
REQ2.2.2 | Used to modify the existing account details of a customer. | Verify that the SSN provided is of length 9 digits | Medium | 2023-10-13 | Version2
REQ2.2.2 | Used to modify the existing account details of a customer. | Verify that the options are provided to the customer to do 1. Last name update, 2. Credit card number update, 3. Full Address Update, 4. Email Update and Phone Update are correct. | Medium | 2023-10-13 | Pass
REQ2.2.2 | Used to modify the existing account details of a customer. | Verify that for credit card number update, the customer info and credit card info tables are updated. | High | 2023-10-13 | Pass
REQ2.2.2 | Used to modify the existing account details of a customer. | Verify that Email provided by the customer is valid | High |  | Version2
REQ2.2.2 | Used to modify the existing account details of a customer. | Verify that Phone number provided by the customer is valid and contains 10 digits | High |  | Version2
REQ2.2.2 | Used to check the existing account details of a customer. | Verify that Last updated column is updated with the current timestamp | High |  | Version2
REQ2.2.2 | Used to check the existing account details of a customer. | Verify that output displayed is only the account updated | High | 2023-10-13 | Pass
REQ2.2.3 | Used to generate a monthly bill for a credit card number for a given month and year. | Verify that the SSN provided is 4 digits (last) | Medium |  | Version2
REQ2.2.3 | Used to generate a monthly bill for a credit card number for a given month and year. | Verify to format the last name provided by the customer is of Title case | Low | 2023-10-11
REQ2.2.3 | Used to generate a monthly bill for a credit card number for a given month and year. | Verify that the credit card number provided is 4 digits(last) | Medium |  | Version2
REQ2.2.3 | Used to generate a monthly bill for a credit card number for a given month and year. | Verify that the month and year collected from the customer is valid | Medium | 2023-10-11 | Pass
REQ2.2.3 | Used to generate a monthly bill for a credit card number for a given month and year. | Verify that the output shown is the current bill for the month and year asked from the customer. | High | 2023-10-11 | Pass
REQ2.2.3 | Used to generate a monthly bill for a credit card number for a given month and year. | Verify that the credit card number is not shown fully | Medium | 2023-10-11 | Pass
REQ2.2.4 | Used to display the transactions made by a customer between two dates. Order by year, month, and day in descending order. | Verify that the Start date and End date are in correct format and valid | Medium | 2023-10-11 | Pass
REQ2.2.4 | Used to display the transactions made by a customer between two dates. Order by year, month, and day in descending order. | Verify that the End date is higher than the Start date | Medium |  | Version2
REQ2.2.4 | Used to display the transactions made by a customer between two dates. Order by year, month, and day in descending order. | Verify that the output displayed is sorted in descending order. | Medium | 2023-10-11 | Pass
REQ3.1 | Find and plot which transaction type has the highest transaction count. | Verify that the plot has Transaction types and the count of Transaction types | Medium | 2023-10-09 | Pass
REQ3.1 | Find and plot which transaction type has the highest transaction count. | Verify that the plot has displayed the highest Transaction count | Medium | 2023-10-09 | Pass
REQ3.2 | Find and plot which state has a high number of customers. | Verify that the plot has the states and no of customers in each state and the highest no of customers is sorted | Medium | 2023-10-09 | Pass
REQ3.3 | Find and plot the sum of all transactions for the top 10 customers, and which customer has the highest transaction amount. | Verify that the plot has top 10 customer names displayed | Medium | 2023-10-09 | Pass
REQ3.3 | Find and plot the sum of all transactions for the top 10 customers, and which customer has the highest transaction amount. | Verify that the plot displayed the transaction amounts | Medium | 2023-10-09 | Pass
REQ4.1 | Create a Python program to GET (consume) data from the above API endpoint for the loan application dataset. | Verify that the extracted data is proper | Medium | 2023-10-05 | Pass
REQ4.2 | Find the status code of the above API endpoint. | Verify that the status code is found out and displayed properly | Medium | 2023-10-05 | Pass
REQ4.3 | Once Python reads data from the API, utilize PySpark to load data into RDBMS (SQL). The table name should be CDW-SAPP_loan_application in the database. Note: Use the “creditcard_capstone” database. | Verify that the data is loaded into the table CDW_SAPP_loan_application. | Medium | 2023-10-05 | Pass
REQ4.3 | Once Python reads data from the API, utilize PySpark to load data into RDBMS (SQL). The table name should be CDW-SAPP_loan_application in the database. Note: Use the “creditcard_capstone” database. | Verify that the table is created in the database creditcard_capstone. | Medium | 2023-10-05 | Pass
REQ5.1 | Find and plot the percentage of applications approved for self-employed applicants. | Verify that the query is selected for the self employed applicants | Medium | 2023-10-09 | Pass
REQ5.1 | Find and plot the percentage of applications approved for self-employed applicants. | Verify that the plot is annotated properly with the % details | Medium | 2023-10-09 | Pass
REQ5.2 | Find the percentage of rejection for married male applicants. | Verify that the query is selected for the Married Male applicants | Medium | 2023-10-09 | Pass
REQ5.2 | Find the percentage of rejection for married male applicants. | Verify that the plot is annotated properly with the % details | Medium | 2023-10-09 | Pass
REQ5.3 | Find and plot the top three months with the largest volume of transaction data. | Verify that the query is written to collect the sum of Transaction value | Medium | 2023-10-09 | Pass
REQ5.3 | Find and plot the top three months with the largest volume of transaction data. | Verify that the plot is is displaying the top 3 months | Medium | 2023-10-09 | Pass
REQ5.4 | Find and plot which branch processed the highest total dollar value of healthcare transactions. | Verify that the query is written to filter the Healthcare Transactions. | Medium | 2023-10-09 | Pass
REQ5.4 | Find and plot which branch processed the highest total dollar value of healthcare transactions. | Verify that the plot is showing the highest Transactions Value in the Descending order | Medium | 2023-10-09 | Pass
REQ5.4 | Find and plot which branch processed the highest total dollar value of healthcare transactions. | Verify that the BRANCH_CITY is displayed properly. | Medium | 2023-10-09 | Pass
REQ5.4 | Find and plot which branch processed the highest total dollar value of healthcare transactions. | Verify that the Transaction Value is dsiplayed in the plot. | Medium | 2023-10-09 | Pass

## Bug report
Defect ID | Defect Description | Steps to reproduce | Severity | State | Created by | Assigned to